## Lilienmatt Budget
LILIENMATT — ANNABERG XXI
Construction Budget — Status 31 October 2025
Source: Annaberg XXI · Lilienmatt progress schedule (signed at shareholder meeting 23.10.2025)
HEADLINE
Total project budget | EUR | 14158750 | EUR — 6 houses + common areas
Completed value (31.10.2025) | EUR | 7086600 | Net of open balance
Open to completion | EUR | 7072150 | Of which EUR 5.67M houses, EUR 1.40M common
Target hand-over |  | 30 Nov 2026 | Houses 1/2/3: 30 Nov 2026 — finishing level outside by May 2026
PER-HOUSE BREAKDOWN
House | Scope | Budget (EUR) | Done (EUR) | Open (EUR) | % Done
House 1 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2220000 | 1353000 | 867000 | 60.95%
House 2 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2275000 | 1341100 | 933900 | 58.95%
House 3 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2115000 | 486750 | 1628250 | 23.01%
House 4 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2055000 | 1282750 | 772250 | 62.42%
House 5 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2050000 | 1284000 | 766000 | 62.63%
House 6 | Envelope · Outside · Fit-out L1+L2 · MEP · Common | 2040000 | 1339000 | 701000 | 65.64%
Subtotal — 6 houses |  | 12755000 | 7086600 | 5668400 | 55.56%
COMMON AREAS & SITE INFRASTRUCTURE
Item | Description | Budget (EUR) | Done (EUR) | Open (EUR) | % Done
Trafo station + outside light | Main trafo + path/stair lighting | 155000 | 23250 | 131750 | 15%
Outside areas — upper row | Gardens, walkways, stairs | 180000 | 117000 | 63000 | 65%
Middle road | Road between two rows of houses | 150000 | 15000 | 135000 | 10%
Outside areas — lower row | Gardens, walkways, stairs | 180000 | 9000 | 171000 | 5%
Access road | Public street to plot | 120000 | 0 | 120000 | 0%
Garage + common areas | Fit-out garage, building access | 650000 | 0 | 650000 | 0%
Snagging / deficiencies | Removal of defects | 100000 | 0 | 100000 | 0%
Documentation / authorities | Hand-over approvals | 10000 | 2000 | 8000 | 20%
Hand-over | Cleaning + functional checks | 25000 | 0 | 25000 | 0%
Subtotal — common |  | 1570000 | 166250 | 1403750 | 10.59%
FUNDING PLAN — agreed at Shareholder Meeting 23.10.2025
Period | Source | Amount (EUR) | Note
27 Oct – 10 Nov 2025 | AO front-load | 2000000 | Required to place orders
October 2025 | AO monthly tranche | 1000000 | Performance month
November 2025 | AO monthly tranche | 1000000 | Performance month
December 2025 | AO monthly tranche | 1000000 | Performance month
January 2026 | AO monthly tranche | 1000000 | Performance month
February 2026 | AO monthly tranche | 1000000 | Performance month
March 2026 | AO monthly tranche | 1000000 | Performance month
Ongoing | Apartment sales | 1072150 | Covers second-level inside finishing
Total funding plan |  | 9072150 | Covers EUR 7,072,150 open balance
NOTES
1. Figures stated net (excl. VAT). Status reflects on-site progress as at 31 October 2025.
2. Project finishing — outside completion targeted May 2026; full hand-over Houses 1/2/3 by 30 November 2026.
3. Funding plan ratified by main shareholder AO at 23.10.2025 meeting: EUR 1.0M / month plus EUR 2.0M front-load.
4. Remaining ~EUR 1.07M of inside finishing (second level) covered by ongoing apartment sales.
5. This summary supersedes prior versions. Underlying ledger: Lilienmatt cashflow statement (status 14.10.2025).
Brisen Capital SA · For internal AO discussion · 4 May 2026