## Lilienmatt Budget
LILIENMATT — ANNABERG XXI
Cost-to-Completion — Status 4 May 2026
Source: Siegfried, on-site update 04.05.2026 (supersedes 23.10.2025 shareholder-meeting baseline)
HEADLINE
Open construction works | EUR | 2850000 | Funded by Lilienmatt (shareholder / Aukera)
Open fit-out | EUR | 3900000 | Not in Oct 2025 plan — funded by apartment buyer payments
Total cost-to-completion | EUR | 6750000 | Construction + fit-out
Target hand-over |  | 30 Nov 2026 | Houses 1/2/3: 30 Nov 2026
OPEN WORKS — Breakdown (status 04.05.2026)
Work package | Scope | Open (EUR) | Funding source
MEP | Sanitary · plumbing · heating · cooling · electrical | 1200000 | Lilienmatt / Aukera
Outside construction | Roads · gardens · pathways · stairs | 500000 | Lilienmatt / Aukera
Façade | Outstanding façade works | 300000 | Lilienmatt / Aukera
Steel balustrade | Handrails · balustrades | 350000 | Lilienmatt / Aukera
Garage | Garage fit-out + access | 500000 | Lilienmatt / Aukera
Construction subtotal |  | 2850000 | Lilienmatt / Aukera
Fit-out (apartments) | Inside finishing · 2nd-level fit-out (tiles, bathrooms, flooring, paintings) | 3900000 | Apartment buyer payments
Total cost-to-completion |  | 6750000 | Construction (Lilienmatt) + fit-out (buyers)
FUNDING SOURCES
Source | Covers | Amount (EUR) | Note
Lilienmatt (shareholder / Aukera) | Construction works (MEP, outside, façade, steel, garage) | 2850000 | Per 23.10.2025 plan + Aukera EUR 15M facility (target close 30 May 2026)
Apartment buyers | Fit-out (inside finishing) | 3900000 | Buyer instalments triggered by sales / handover — outside Oct 2025 plan
Total funding required |  | 6750000 | Matches total cost-to-completion
NOTES
1. Figures stated net (excl. VAT). Status reflects on-site progress as at 4 May 2026 (Siegfried).
2. Project finishing — outside completion targeted May 2026; full hand-over Houses 1/2/3 by 30 November 2026.
3. Construction works (EUR 2.85M) funded by Lilienmatt — covered by shareholder funding plan ratified 23.10.2025 plus Aukera EUR 15M facility.
4. Fit-out (EUR 3.9M) is NEW — not included in October 2025 shareholder meeting. Funding source: apartment buyer instalments.
5. This summary supersedes the 31.10.2025 baseline.
Brisen Capital SA · For internal AO discussion · 4 May 2026