## Aelios
| FINANCING TO COMPLETION 2025–2026 |  |  | As of 13 Jun 2025 | [7 empty] | As of 09 Apr 2026
A | Allocation |  |  | 2025 ( MAR-SEP) | [7 empty] | 2025 ( OCT-DEC) |  | 2026 (JAN-JUN)
|  |  | ACTUAL |  |  | PROJECTED |  |  |  | CAPITAL CALL |  | ACTUAL SPENT | DEFICIT OF FUNDS | PROJECTED & ACTUAL | DEFICIT OF FUNDS AND PROJECTED TILL JUNE 2026 | CAPITAL CALL
| Description | % | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | Sep 2025 |  | OCT-DEC | DIFFERENCE BTW REQUESTED & RECEIVED | Jan2026 -June 2026 | OCT -JUNE 2026 | Apr 2026
Uses
| Available at begining of period |  | 14814554 | 8723948 | 711925.6708 | -0.32917 |  | 0 | 0
CAPEX
| Construction and Development |  | -4320606 | -6261022.3292 | -6361022.3292 | -7002685.3292 | -5026592.8125 | -1098625 | -1670000 | -31740553.8 |  | -1341458.08 |  | -2541213
| Hotel Replacement Construction Costs | [8 empty] | 0 |  |  |  | -1050000
| Appartments Replacement Construction Costs | [8 empty] | 0 |  |  |  | -1500000
OPEX
| Settlement and Warranty Fund | [8 empty] | 0 |  |  |  | -4000000
| Mandarin Hotel Pre-Opening Costs |  | -340000 | -400000 | -550000 | -1150000 | -1110000 | -1110000 | -980000 | -5640000
| Hotel Staff |  | -160000 | -190000 | -290000 | -890000 | -850000 | -850000 | -850000 | -4080000 |  | -1700000 |  | 0
| Marketing HotelCo and preopening costs |  | -180000 | -210000 | -260000 | -260000 | -260000 | -260000 | -130000 | -1560000 |  | -136000 |  | -225000
| Marketing AppartCo ( not yet calculated) | [8 empty] | 0 |  | 0 |  | 0
| Working Capital liquidity Hotel | [8 empty] | 0 |  | 0 |  | -1500000
| OS&E,IT and ART |  | -1150000 | -1071000 | -350000 | -150000 | 0 | 0 | 0 | -2721000 |  | -851987 |  | -395295
| sales Fee, property management | [8 empty] | 0 |  | -1143556 |  | -703531
| Bank Interests |  |  | 0 | 0 | 0 | -3000000 | 0 | 0 | -3000000 |  | -1049140 |  | -3375964
| VAT and Taxes |  | -280000 | -280000 | -280000 | -280000 | 0 | 0 | 0 | -1120000 |  | 373300 |  | -5770000
| Total Uses |  | -6090606 | -8012022.3292 | -7541022.3292 | -8582685.3292 | -9136592.8125 | -2208625 | -2650000 | -44221553.8
Sources
| Bank Finance |  | 6090606 | 8012022 | 711926 | 0 | 0 | 0 | 0 | 14814554
| Sales of Appartments | [8 empty] | 0 |  |  |  | 4430118
| S'Holder Total Capital Injection |  |  |  | 6829096.3292 | 8582685.3292 | 9136592.8125 | 2208625 | 2650000 | 29406999.4708
| Fund ( 52%) Actual Capital Injection | 52% |  | 0 | 3551130.0912 | 4462996.3712 | 4751028.2625 | 1148485 | 1378000 | 15291639.7248
| Aelios (48%) Actual Capital Injection | 48% |  | 0 | 0 | 0 | 4800000 | 1060140 | 1272000 | 14115359.746 |  |  |  | 2500000
| Total Sources |  | 6090606 | 8012022 | 7541022.3292 | 8582685.3292 | 9136592.8125 | 2208625 | 2650000 | 29406999.4708
| Balance at the end of period |  |  | -0.32917 | 0 | 0 | 0 | 0 | 0
B | Aelios (48%) |  |  |  |  | If no income from sales of appartments untill September 2025
| Aelios Contractually Due Capital Injection |  | 3033393 |  | 3277966.238 | 4119688.958 | 4385564.55 | 1060140 | 1272000 | 17148752.746
| Aelios Contractual due for Shares of Appartco |  |  | 5800000 | [5 empty] | 5800000
| Total Pmts |  | 3033393 | 5800000 | 3277966.238 | 4119688.958 | 4385564.55 | 1060140 | 1272000 | 22948752.746
| Aelios Actually Invested & Agreed |  | 0 | 5500000 | 0 | 0 | 4800000 |  |  | 10300000
| Aelios Overdue |  | 3033393 | 300000 | 3277966.238 | 4119688.958 | -414435.45 | 1060140 | 1272000 | 12648752.746
| Aelios Accumulative Overdue |  | 3033393 | 3333393 | 6611359.238 | 10731048.196 | 10316612.746 | 11376752.746 | 12648752.746 | 12648752.746
C | Fund ( 52%) |  |  |  |  | If no income from sales of appartments untill September 2025
| Fund Contractually due Capital Injection |  | 0 | 0 | -3551130.0912 | -4462996.3712 | -4751028.2625 | -1148485 | -1378000
| Fund Actually Invested |  | 3033393 | 0 | 3551130.0912 | 4462996.3712 | 4751028.2625 | 1148485 | 1378000
| Fund Over-invested |  | 3033393 | 0 | 0 | 0 | -414435.45 | 1060140 | 1272000 | 4951097.55
| Fund Over-invested Accumulated |  | 3033393 | 3033393 | 3033393 | 3033393 | 2618957.55 | 3679097.55 | 4951097.55 | 4951097.55
|  |  | Funding Provided by the Parties ( before opening) | [5 empty] | Funding 1 and Funding 2 Provided by the Parties ( post opening)
|  |  | Parties | by 31.06.2025 |  | by 31.10.2025 |  |  | Parties | 31.09.2025 - 31.12.2025 |  | 31.12.2025 - 31.03.2026
|  |  |  | Required Funding | Parties Loans Provided | Required Funding | Parties Loans Provided |  |  | Required Additional Funding 1 | Parties Loans Provided | Required Additional Funding 2 | Parties Loans Provided
|  |  | Fund (52%) | 15291640 | 15333393 | 18577815 | 18577815 |  | Fund (52%) | 3041397.3616 | 5738338.951 | 2539295.72 | 2383261
|  |  | Aelios (48%) | 14115360 | 4800000 | 17148752 | 17148752 |  | Aelios (48%) | 2807443.7184 | not provided | 2343965.28 | 2500000
|  |  | Total for the Period | 29407000 | 20133393 | 35726567 | 35726567 |  | Total for the Period | 5848841.08 | 5738338.95 | 4883261 | 4883261
|  |  | Required Funding by the Parties ( April Jun 2026) | [5 empty] | Parties Funding per OPEX/CAPEX
|  |  | Parties | by 31.03.2026 |  |  |  |  | Asset Allocation | by 31.06.2025 | from 31.09.2025 till 31.12.2025 | from 31.12.2025 till 31.03.2026 | from 31.03.2026 till 31.06.2026
|  |  |  | Provided | Should Have been Provided | Required Additional Funding | Parties Loans to be Provided ( incl Disbalance Rectification) |  | CAPEX | 18531958.4906 | 1341458.08 | 1167984.51 | 2143811.79
[9 empty] | OPEX | 10875041.5094 | 4507383 | 3715276.49 | 6819314.34
|  |  | Fund (52%) | 8121599.95 | 5580693.0816 | 4660825.5876 | 2062457.61
|  |  | Aelios (48%) | 2500000 | 5151408.9984 | 4302300.5424 | 6900668.52
|  |  | Total for the Period | 10621599.95 | 10732102.08 | 8963126.13 | 8963126.13
|  |  | SOURCES OF FUNDING — How the EUR 27,134,844 is Covered | [5 empty] | CAPEX - Finishing Construction
[9 empty] | Capital Required | Description | Oct-Dec2025 | Jan-Jun 2026 | Total Oct-Jun
|  |  | Source | Oct-Dec 2025 | Jan-Mar 2026 | Apr-Jun 2026 | Total |  | Construction Hotel | → Overran EUR 1.34M from 2-month delay (Sep→Nov opening). Ongoing works to completion. | -1341458.08 | -2541213 | -3882671.08
|  |  | Fund (52%) | [5 empty] | Defects Hotel | → Post-Hagenauer insolvency. Hotel defects repaired at own cost. Electrical audit EUR 250-300K before May 26 inspection. | 0 | -1050000 | -1050000
|  |  | Aelios (48%) | [5 empty] | Finish Appartments | → Windows, KNX, electrical defects. New contractors at full price — Hagenauer subcontractors refuse to return. | 0 | -1050000 | -1050000
[9 empty] | Capex Sub Total |  | -1341458.08 | -5091213 | -6432671.08
Parties Total
OPEX- Hotel Business
|  |  | Apartment Sales Proceeds | 0 |  |  |  |  | Capital Required | Description | Oct-Dec2025 | Jan-Jun 2026 | Total Oct-Jun
|  |  | Total | [5 empty] | Hotel Staff | Staff hired for Sep opening. Continued drawing salaries through Nov. EUR 850K/month × 2 delay months. | -1700000 | 0 | -1700000
[9 empty] | MO Marketing | Marketing paused during delay — resumed Q1 2026. | -136000 | -225000 | -361000
|  |  | Expected Capital Tranches (Apr–Jun 2026) |  |  |  |  | % of Parties Capital | Warranties | Hagenauer EUR 19M claim. Settlement, 3-year guarantees, legal costs. | 0 | -4000000 | -4000000
|  |  | Month | April 2026 | May 2026 | June 2026 | Total Provided by Parties Oct 2025 – Jun 2026 |  | Working Capital Hotel (NEW) | MO contractual right to EUR 1.5M reserve. Daily operations (food, supplies, salaries). | 0 | -1500000 | -1500000
Fund (52%)
|  |  | Aelios (48%) | 2500000 | 2500000 |  |  |  | OS&E, IT, Art | Over-budget IT systems (EUR 319K — PMS, WiFi, smart room). Art EUR 105K. | -851987 | -395295 | -1247282
[9 empty] | Sales Fees & Property Management | Apartment sales commissions (1.5–2%) + property management. Sales started after construction. | -1143556 | -703531 | -1847087
[9 empty] | Bank Interest (Aukera) | Senior facility 5.4% p.a. EUR 350–500K/month. Higher due to extended drawdown from delay. | -1049140 | -3375964 | -4425104
[9 empty] | VAT & Taxes (NEW LAW) | Nov 2025 Betrugsbekämpfungsgesetz. Luxury apartments >EUR 2.5M lose VAT exemption. EUR 5.77M hit. | 373300 | -5770000 | -5396700
[9 empty] | OPEX SUBTOTAL |  | -4507383 | -15969790 | -20477173
[9 empty] | TOTAL CAPITAL REQUIRED (Oct 2025 – Jun 2026) |  | -5848841.08 | -21286003 | -27134844.08
Note on G85: PAID — AO April DR#1 fulfilled. Settlement 24-27 Apr 2026 (mixed-source): • USD 700K bridged from DV UBS Swiss private (Fri 24 Apr 2026) • USD 1.8M from AO's Armenia account (27 Apr 2026) Eli→LCG payment orders executed 28 Apr 2026. Field-validated AO Baden-Baden 2026-05-04. See curated/2026-05-04-ao-capital-call-7m-walkthrough.md.

## BC Rev TL CF
Equity Requirements Calculations V1
Internal notes / BC
Date: 13.9.2024 | June 3-9 | June 17-21 | June 24-30 | July 8-14 | July 22-25 | August 5-11 | Sept. 2-8 | Oct 1-4 | Nov 4-8 | Dec 2-6 | Jan 1-3 | Feb 3-6 | March 3-6 | Apr 1-4 | May 5-8 | June 2-5 | July 1-4 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | 2002-01-01 | 2002-02-01 | 2002-03-01 | 2002-04-01 | 2002-05-01 | 2002-06-01 | Total from March 2025 -Dec 2025 | Jan 2026-June 2026 | TOTAL | TOTAL outstanding |  |  | SUMMARY POSITION FROM TL
[35 empty] | OUTGOINGS |  | 2026-04-01 | 2026-05-01 | 2026-06-01 | Q2 Total
Balance begining of period | [35 empty] | Type
[34 empty] | update date | MOVIE Development works
Payments | [33 empty] | identify OB locations | Hotel / HAG replacement | Soft accrual
Hagenauer Fit out | -6025000 | -2447500 | 0 | -5625500 | -5801526 |  | -4129588 | -1070089 | -1557241 | -3356909 | -2515021 | -2137684 | -1170136 | -2195244 | -1344630 | -1051978 | -1733414 | -1693227 |  | -435140.62 | -1806961 | [12 empty] | reconcile with Bs | Residences / HAG replacement | Soft accrual
Hagenauer FF&E | [8 empty] | -300000 | -221437 |  |  | -450935 | -1076933 | -610739 | -1192113 | -934072 | -1069427 | -1111918 | -575996.4 | -328000 | [12 empty] | split to weekly | Residences / Standard works | What is this
Hagenauer HKLS | [7 empty] | -1116499 | -1230237 | -1507803 | -1638885 | -1211618 | -1044657 | -886555 | -814962 | -898260 | -1104626 | -767953 | -883132 | -179797 | -100000 | [12 empty] | what is open A/P now? | Kitchen / Terraces / Eng Bauer | What is this
Hagenauer Damage claim deduction | [20 empty] | 2330000 | [12 empty] | What is soft accrual? | Brisen Development costs | Hard accrual
Hagenauer TU Fee | [7 empty] | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -132822 | -100000 | -100000 | -100000 | -100000 | [11 empty] | Should the net equity requirements only? | VAT recon of past
Hotel replacement Hagenauer | [25 empty] | -350000 | -350000 | -350000 | [5 empty] | Are the CF items net of VAT? | MOVIE Hotel operations
Apartments standard | [7 empty] | -48625 | [8 empty] | -114053 | -510696 |  |  | -226092.69 | 0 | -139034 |  |  | -550000 | -550000 | -550000 | [5 empty] | Review BD costs | Preopening payables
Apartments replacment of Hagenauer | [25 empty] | -150000 | -150000 | -150000 | [5 empty] | is this Hotel subcontractors? | Property Management
kitchen/terraces/facade/Engelmann Bauer | [9 empty] | -231851 |  | -347953 |  |  | -85568 |  |  | -267200 | [6 empty] | -138216 |  |  | -150000 | [5 empty] | 80k pm sales or PM fee? | Operations funding / shortfall
sales Fee, property management | [15 empty] | -24550.24 |  | -172961 | -80000 |  |  |  | -110000 |  | -353531 | [8 empty] | Split BD costs to Dev / Ops
Development Cost | [7 empty] | -375098 | -348820 |  | -305755 |  | -365175 | -357968 | -319469 |  |  | -296047 |  |  |  |  | -385141 | -173180 | -237256 | -350000 | -350000 | -350000 | [5 empty] | Aukera interest is quaterly | Taxes
Art | [15 empty] | -31112 | -4903 |  | -21669 | [14 empty] | Reconcile Loan / Equity from Sales | VAT outgoing
OS&E,fitness including VAT | [12 empty] | -465000 |  |  |  | -150000 | -55279 |  |  | -55279 |  | -11513 | -18426 | [10 empty] | VAT incoming
IT | [9 empty] | -122058 | [8 empty] | -28068 |  | -59541 | -180827 | -262812 | -102544
Mandarin Pre-Opening employees | [6 empty] | -250000 |  |  |  | -100000 | -300000 |  | -150000 | -200000 | -390000 | -371000 | -850000 | -817000 | -890000 | -1400000 | [13 empty] | Aukera Senior Lending
Mandarin Pre-Opening Marketing and other Costs / Consumables | [11 empty] | -180000 |  | -160000 | -150000 | -415000 | -370000 | -195000 | -433000 | -110000 | -400000 | -175000 |  |  |  | -225000 | [8 empty] | Interest | Should be monthly
Working Capital liquidity Hotel | [25 empty] | -600000 | [8 empty] | Principal repayment
Interest Reserve have to be finance from Equity or Sales only |  |  |  | -3375000 | [5 empty] | -4040000 | [8 empty] | -2035640 |  |  | -2013500 |  |  | -1775963.81 |  |  | -1600000
VAT and Taxes |  |  |  |  | -1132500 | [20 empty] | -219000 | [8 empty] | OUTGOINGS TOTAL
Total Payments
Funding ideas
Sources | [33 empty] | Reconcile Loan / Equity from Sales | to negotiate 1.5m loan from Aukera
Sales |  |  | 3800000 | [13 empty] | 6000000 |  |  |  |  | 3120000 |  | 4430118 | [9 empty] | Aukera Annaberg loan | on current sale of 3 apartments | 1753800
Special Requests, interests Cupial, Sales Fee | [6 empty] | 110000 | 50000 | 66000 |  |  |  | 48546 |  |  |  |  | 276200 |  |  |  |  | 132000 |  | 482566 |  | 100000 | [6 empty] | MO Fee settlement | to negotiate 1.5m loan from MO
Release of Cash LIST, HAG 5% retention money
Equity |  | 610000 |  | 4320000 |  | 2100000 |  |  |  | 4040000 | [15 empty] | 2000000 | 2000000 | 3000000
Add. Auera Finance | 7380000 |  |  |  | 10000000 | [6 empty] | 30000000
Total Finance
Balance at the end of period
Comments | MOHG marketing licence Fee 3,945 mio EUR due in Dec 2025 after handover of the apartments - not included in this CF!
registration mortage Fee 2,0 mio EUR is not included - unclear when court decicion will occur
Hagenauer replacement cost for Hotel are not assessed yet

## Equity calculation
Equity Requirements Calculations V1
Date: 13.9.2024 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | TOTAL outstanding
Balance begining of period
Payments
Hagenauer Fit out | -6025000 | -2447500 | 0 | -5625500 | -5801526 |  | -4129588 | -1070089 | -1557241 | -3356909 | -2515021 | -2137684 | -1170136 | -2195244 | -1344630 | -1051978 | -1733414 | -1693227 |  | -435140.62 | -1806961
Hagenauer FF&E | 2024-11-01: -300000; 2024-12-01: -221437; 2025-03-01: -450935; 2025-04-01: -1076933; 2025-05-01: -610739; 2025-06-01: -1192113; 2025-07-01: -934072; 2025-08-01: -1069427; 2025-09-01: -1111918; 2025-10-01: -575996.4; 2025-11-01: -328000
Hagenauer HKLS | 2024-10-01: -1116499; 2024-11-01: -1230237; 2024-12-01: -1507803; 2025-01-01: -1638885; 2025-02-01: -1211618; 2025-03-01: -1044657; 2025-04-01: -886555; 2025-05-01: -814962; 2025-06-01: -898260; 2025-07-01: -1104626; 2025-08-01: -767953; 2025-09-01: -883132; 2025-10-01: -179797; 2025-11-01: -100000
Hagenauer Damage claim deduction | 2025-11-01: 2330000
Hagenauer TU Fee | [7 empty] | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -398466 | -132822 | -100000 | -100000 | -100000 | -100000 |  |  |  |  | -350000 | -350000 | -350000
Hotel replacement Hagenauer
Apartments standard | 2024-10-01: -48625; 2025-07-01: -114053; 2025-08-01: -510696; 2025-11-01: -226092.69; 2025-12-01: 0; 2026-01-01: -139034; 2026-04-01: -550000; 2026-05-01: -550000; 2026-06-01: -550000
Apartments replacment of Hagenauer | 2026-04-01: -150000; 2026-05-01: -150000; 2026-06-01: -150000
kitchen/terraces/facade/Engelmann Bauer | 2024-12-01: -231851; 2025-02-01: -347953; 2025-05-01: -85568; 2025-08-01: -267200; 2026-03-01: -138216; 2026-06-01: -150000
sales Fee, property management | 2025-06-01: -24550.24; 2025-08-01: -172961; 2025-09-01: -80000; 2026-01-01: -110000; 2026-03-01: -353531
Development Cost | 2024-10-01: -375098; 2024-11-01: -348820; 2025-01-01: -305755; 2025-03-01: -365175; 2025-04-01: -357968; 2025-05-01: -319469; 2025-08-01: -296047; 2026-01-01: -385141; 2026-02-01: -173180; 2026-03-01: -237256; 2026-04-01: -350000; 2026-05-01: -350000; 2026-06-01: -350000
Art | 2025-06-01: -31112; 2025-07-01: -4903; 2025-09-01: -21669
OS&E,fitness including VAT | 2025-03-01: -465000; 2025-07-01: -150000; 2025-08-01: -55279; 2025-11-01: -55279; 2026-01-01: -11513; 2026-02-01: -18426
IT | 2024-12-01: -122058; 2025-09-01: -28068; 2025-11-01: -59541; 2025-12-01: -180827; 2026-01-01: -262812; 2026-02-01: -102544
Mandarin Pre-Opening employees | 2024-09-01: -250000; 2025-01-01: -100000; 2025-02-01: -300000; 2025-04-01: -150000; 2025-05-01: -200000; 2025-06-01: -390000; 2025-07-01: -371000; 2025-08-01: -850000; 2025-09-01: -817000; 2025-10-01: -890000; 2025-11-01: -1400000; 2026-04-01: -225000
Mandarin Pre-Opening Marketing and other Costs / Consumables | 2025-02-01: -180000; 2025-04-01: -160000; 2025-05-01: -150000; 2025-06-01: -415000; 2025-07-01: -370000; 2025-08-01: -195000; 2025-09-01: -433000; 2025-10-01: -110000; 2025-11-01: -400000; 2025-12-01: -175000
Working Capital liquidity Hotel | 2026-04-01: -600000
Interest Reserve have to be finance from Equity or Sales only | 2024-06-01: -3375000; 2024-12-01: -4040000; 2025-09-01: -2035640; 2025-12-01: -2013500; 2026-03-01: -1775963.81; 2026-06-01: -1600000
VAT and Taxes | 2024-07-01: -1132500; 2026-04-01: -219000
Total Payments
Sources
Sales | 2024-05-01: 3800000; 2025-07-01: 6000000; 2025-12-01: 3120000; 2026-02-01: 4430118
Special Requests, interests Cupial, Sales Fee | 2024-09-01: 110000; 2024-10-01: 50000; 2024-11-01: 66000; 2025-03-01: 48546; 2025-08-01: 276200; 2026-01-01: 132000; 2026-03-01: 482566; 2026-05-01: 100000
Release of Cash LIST, HAG 5% retention money
Equity | 2024-04-01: 610000; 2024-06-01: 4320000; 2024-08-01: 2100000; 2024-12-01: 4040000; 2026-04-01: 2000000; 2026-05-01: 2000000; 2026-06-01: 3000000
Add. Auera Finance | 2024-03-01: 7380000; 2024-07-01: 10000000; 2025-02-01: 30000000
Total Finance
Balance at the end of period
Comments | 2024-03-01: MOHG marketing licence Fee 3,945 mio EUR due in Dec 2025 after handover of the apartments - not included in this CF!
registration mortage Fee 2,0 mio EUR is not included - unclear when court decicion will occur
Hagenauer replacement cost for Hotel are not assessed yet

## progress of works
Progress of works
|  |  | Fit out planned | Fit out actual | FF&E planned | FF&E actual | HKLS planned | HKLS actual | TU Fees paid
| TOTAL | TOTAL
| planned | actual + Forecast
2024-09-01 | 76688142 |  |  | 59059138 | 2663064 | 2663064 |  | 14965940 | 12824766 | progress of works per end of September
2024-10-01 |  |  |  | 1703950 |  | 300000 |  | 1230237 | 431798.89 | 398466
2024-11-01 |  |  |  | 3356909 |  | 221437 |  | 1507803 | 431798.89 | 398466
2024-12-01 |  |  |  | 2515021 |  |  |  | 1638885 | 431798.89 | 398466
2025-01-01 |  |  |  | 2137684 |  |  |  | 1211618 | 431798.89 | 398466
2025-02-01 |  |  |  | 1170136 |  | 450935 |  | 1044657 | 431798.89 | 398466
2025-03-01 |  |  |  | 2195244 |  | 1076933 |  | 886555 | 431798.89 | 398466
2025-04-01 |  |  |  | 1344630 |  | 610739 |  | 814962 | 431798.89 | 398466
2025-05-01 |  |  |  | 1051978 |  | 1192113 |  | 898260 | 431798.89 | 398466
2025-06-01 |  |  |  | 1733414 |  | 934072 |  | 1104626 | 431798.89 | 132822
2025-07-01 |  |  |  | 1693227 |  | 1069427 |  | 767953 |  | 100000
2025-08-01 | [5 empty] | 1111918 |  | 883132 |  | 100000
2025-09-01 |  |  |  | 435140.62 |  | 575996.4 |  | 179797 |  | 100000
2025-10-01 |  |  |  | 1806961 |  | 328000 |  | 100000
TOTAL |  |  |  |  | 12226961 |  |  |  | 16710956
works open

## Aelios McKinsey
| FINANCING TO COMPLETION 2025–2026 |  |  |  | As of 13 Jun 2025 | [8 empty] | As of 09 Apr 2026
A | Allocation |  |  |  | 2025 ( MAR-SEP) | [8 empty] | 2025 ( OCT-DEC) |  | 2026 (JAN-JUN)
|  |  | ACTUAL |  |  |  | PROJECTED |  |  |  |  | CAPITAL CALL |  | ACTUAL SPENT | DEFICIT OF FUNDS | PROJECTED & ACTUAL | DEFICIT OF FUNDS AND PROJECTED TILL JUNE 2026 | CAPITAL CALL
| Description | % | MARCH |  | APRIL | MAY | JUNE | JULY | AUGUST |  | SEPTEMBER | Sep 2025 |  | OCT-DEC | DIFFERENCE BTW REQUESTED & RECEIVED | Jan2026 -June 2026 | OCT -JUNE 2026 | Apr 2026
Uses
| Available at begining of period |  | 14814554 |  | 8723948 | 711925.6708 | -0.32917 |  | 0 |  | 0
CAPEX
| Construction and Development |  | -4320606 |  | -6261022.3292 | -6361022.3292 | -7002685.3292 | -5026592.8125 | -1098625 |  | -1670000 | -31740553.8 |  | -1341458.08 |  | -2541213
| Hotel Replacement Construction Costs | [10 empty] | 0 |  |  |  | -1050000
| Appartments Replacement Construction Costs | [10 empty] | 0 |  |  |  | -1500000
OPEX
| Settlement and Warranty Fund | [10 empty] | 0 |  |  |  | -4000000
| Mandarin Hotel Pre-Opening Costs |  | -340000 |  | -400000 | -550000 | -1150000 | -1110000 | -1110000 |  | -980000 | -5640000
| Hotel Staff |  | -160000 |  | -190000 | -290000 | -890000 | -850000 | -850000 |  | -850000 | -4080000 |  | -1700000 |  | 0
| Marketing HotelCo and preopening costs |  | -180000 |  | -210000 | -260000 | -260000 | -260000 | -260000 |  | -130000 | -1560000 |  | -136000 |  | -225000
| Marketing AppartCo ( not yet calculated) | [10 empty] | 0 |  | 0 |  | 0
| Working Capital liquidity Hotel | [10 empty] | 0 |  | 0 |  | -1500000
| OS&E,IT and ART |  | -1150000 |  | -1071000 | -350000 | -150000 | 0 | 0 |  | 0 | -2721000 |  | -851987 |  | -395295
| sales Fee, property management | [10 empty] | 0 |  | -1143556 |  | -703531
| Bank Interests |  |  |  | 0 | 0 | 0 | -3000000 | 0 |  | 0 | -3000000 |  | -1049140 |  | -3375964
| VAT and Taxes |  | -280000 |  | -280000 | -280000 | -280000 | 0 | 0 |  | 0 | -1120000 |  | 373300 |  | -5770000
| Total Uses |  | -6090606 |  | -8012022.3292 | -7541022.3292 | -8582685.3292 | -9136592.8125 | -2208625 |  | -2650000 | -44221553.8
Sources
| Bank Finance |  | 6090606 |  | 8012022 | 711926 | 0 | 0 | 0 |  | 0 | 14814554
| Sales of Appartments | [10 empty] | 0 |  |  |  | 4430118
| S'Holder Total Capital Injection |  |  |  |  | 6829096.3292 | 8582685.3292 | 9136592.8125 | 2208625 |  | 2650000 | 29406999.4708
| Fund ( 52%) Actual Capital Injection | 52% |  |  | 0 | 3551130.0912 | 4462996.3712 | 4751028.2625 | 1148485 |  | 1378000 | 15291639.7248
| Aelios (48%) Actual Capital Injection | 48% |  |  | 0 | 0 | 0 | 4800000 | 1060140 |  | 1272000 | 14115359.746 |  |  |  | 2500000
| Total Sources |  | 6090606 |  | 8012022 | 7541022.3292 | 8582685.3292 | 9136592.8125 | 2208625 |  | 2650000 | 29406999.4708
| Balance at the end of period |  |  |  | -0.32917 | 0 | 0 | 0 | 0 |  | 0
B | Aelios (48%) | [5 empty] | If no income from sales of appartments untill September 2025
| Aelios Contractually Due Capital Injection |  | 3033393 |  |  | 3277966.238 | 4119688.958 | 4385564.55 | 1060140 |  | 1272000 | 17148752.746
| Aelios Contractual due for Shares of Appartco |  |  |  | 5800000 | [6 empty] | 5800000
Total Pmts
| Aelios Actually Invested & Agreed |  | 0 |  | 5500000 | 0 | 0 | 4800000 |  |  |  | 10300000
Aelios Overdue
Aelios Accumulative Overdue
C | Fund ( 52%) | [5 empty] | If no income from sales of appartments untill September 2025
| Fund Contractually due Capital Injection |  | 0 |  | 0 | -3551130.0912 | -4462996.3712 | -4751028.2625 | -1148485 |  | -1378000
| Fund Actually Invested |  | 3033393 |  | 0 | 3551130.0912 | 4462996.3712 | 4751028.2625 | 1148485 |  | 1378000
| Fund Over-invested |  | 3033393 |  | 0 | 0 | 0 | -414435.45 | 1060140 |  | 1272000 | 4951097.55
Fund Over-invested Accumulated
|  |  | Funding Provided by the Parties (before opening) | [6 empty] | Funding 1 and Funding 2 Provided by the Parties (post opening)
|  |  | Parties |  | by 31.06.2025 |  | by 31.10.2025 |  |  |  | Parties | 31.09.2025 – 31.12.2025 |  | 31.12.2025 – 31.03.2026
[5 empty] | Required Funding | Parties Loans Provided | Required Funding | Parties Loans Provided |  |  |  | Required Additional Funding 1 | Parties Loans Provided | Required Additional Funding 2 | Parties Loans Provided
|  |  | Fund (52%) |  |  | 15333393 | 18577815 | 18577815 |  |  | Fund (52%)
|  |  | Aelios (48%) |  |  | 4800000 | 17148752 | 17148752 |  |  | Aelios (48%) |  | not provided
|  |  | Total for the Period | [7 empty] | Total for the Period
|  |  | Required Funding by the Parties (April–June 2026) | [7 empty] | Parties Funding per OPEX/CAPEX
|  |  | Parties |  | by 31.03.2026 | [5 empty] | Asset Allocation | by 31.06.2025 | from 31.09.2025 to 31.12.2025 | from 31.12.2025 to 31.03.2026 | from 31.03.2026 to 31.06.2026
[5 empty] | Provided | Should Have Been Provided | Required Additional Funding | Loans to be Provided (incl. Imbalance Rectification) |  |  | CAPEX | 18531958.4906
[11 empty] | OPEX | 10875041.5094
Fund (52%)
Aelios (48%)
Total for the Period
|  |  | SOURCES OF FUNDING — How the EUR 27,134,844 is Covered | [7 empty] | CAPEX — Finishing Construction
[11 empty] | Capital Required | Description | Oct–Dec 2025 | Jan–Jun 2026 | Total Oct–Jun
|  |  | Source |  | Oct–Dec 2025 | Jan–Mar 2026 | Apr–Jun 2026 | Total |  |  | Hotel Construction | → Overran EUR 1.34M from 2-month delay (Sep→Nov opening). Ongoing works to completion.
|  |  | Fund (52%) | [7 empty] | Hotel Defects | → Post-Hagenauer insolvency. Hotel defects repaired at own cost. Electrical audit EUR 250–300K before May 26 inspection.
|  |  | Aelios (48%) | [7 empty] | Finish Apartments | → Windows, KNX, electrical defects. New contractors at full price — Hagenauer subcontractors refuse to return.
CAPEX Subtotal
Parties Total
OPEX — Hotel Business
|  |  | Apartment Sales Proceeds |  | 0 | [5 empty] | Capital Required | Description | Oct–Dec 2025 | Jan–Jun 2026 | Total Oct–Jun
|  |  | Total | [7 empty] | Hotel Staff | Staff hired for Sep opening. Continued drawing salaries through Nov. EUR 850K/month × 2 delay months.
[11 empty] | MO Marketing | Marketing paused during delay — resumed Q1 2026.
|  |  | Expected Capital Tranches (Oct 2025 – Jun 2026) | [5 empty] | % of Parties Capital |  | Warranties | Settlement, 3-year guarantees, legal costs. May not be required in full.
|  |  | Month | Oct 2025 – Mar 2026 | April 2026 | May 2026 | June 2026 | Total Oct 2025 – Jun 2026 |  |  | Working Capital Hotel (NEW) | MO contractual right to EUR 1.5M reserve. Daily operations (food, supplies, salaries).
Fund (52%)
|  |  | Aelios (48%) |  | 2500000 | 2500000 |  |  |  |  | OS&E, IT, Art | Over-budget IT systems (EUR 319K — PMS, WiFi, smart room). Art EUR 105K.
[11 empty] | Sales Fees & Property Management | Apartment sales commissions (1.5–2%) + property management. Sales started after construction.
[11 empty] | Bank Interest (Aukera) | Senior facility 5.4% p.a. EUR 350–500K/month. Higher due to extended drawdown from delay.
[11 empty] | VAT & Taxes (NEW LAW) | Nov 2025 Betrugsbekämpfungsgesetz. Luxury apartments >EUR 2.5M lose VAT exemption. EUR 5.77M hit.
OPEX SUBTOTAL
TOTAL CAPITAL REQUIRED (Oct 2025 – Jun 2026)